## Sheet1
Bug ID | Section / Path | Bug / Concern Description | Status | Priority | Tester Name | Developer Name | Screenshot | Comment
#01 | Home Page | The spelling of Introduction is written Intoduction. The correct spelling should be Introduction. | New | Low | Rochona / Nawar | Rubya
#02 | Home Page | The color of category names does not match with website theme. The color should match with the website theme. | In Progress | Low | Rochona / Nawar | Rubya
#03 | Home Page | The category names are overlapping although clickable. The category names should not overlap. | In Progress | Low | Rochona | Rubya
#04 | Home Page | The logo of the Home Page is distorted. The logo should be clear. | Dev Done | High | Rochona / Nawar | Rubya |  | Test Done - Rochona Test Done - Nawar Dev Done - Rubya
#05 | Sign In | The login button is not working. The login button should work properly. -Username, Password | Test Done | High | Rochona / Nawar | Rubya |  | Test Done - Rochona Test Done - Nawar
#06 | Sign up -> Name | Name field accepts digits. Name should only accept alphabets. -Username, Password | Test Done | Low | Rochona / Nawar | Rubya |  | Test Done - Rochona Test Done - Nawar
#07 | Sign up -> Mobile Number | Mobile Number field accepts less than 11 digits. This field should accept 11 digits only. -Username, Password | New | High | Nawar | Rubya
#08 | Add to cart | Products in the cart are removed when user logs out. The cart items should be saved even user logs out. -Username, Password | In Progress | High | Rochona / Nawar | Rubya |  | Test Done - Rochona Test Done - Nawar
#09 | Order -> Payment | The products added to the cart are not visible on the payment page. The products should be visible while on the payment page. -Username, Password | Test Done | High | Rochona / Nawar | Rubya |  | Test Done - Rochona Test Done - Nawar
#10 | Home Page -> Career | The career page is showing 404 Not Found Error. The page should be accessible. | New | Medium | Rochona / Nawar | Rubya